DXC AI READINESS DIAGNOSTIC

MVP Scope and 3-Week Build Plan

Owner  Chris Bryson, Senior Partner, DXC AdvisoryX

Date  June 2026

Window  Three weeks from kickoff

Capacity  3 to 4 engineers plus the working group

Basis  PRD V5 and Companions 01 to 05

The goal

In three weeks, prove the Diagnostic works and start using it for real. Three outcomes define done: the technology runs end to end, the process around it holds, and an internal customer-zero engagement is underway.

Technology. Prove the technology. The adaptive interview engine conducts the AI Readiness interview, by chat and by voice, and the pipeline turns it into a scored scorecard a partner reviews.

Process. Prove the process. The authoring, run-time pacing, scoring, partner review, and consent steps work as a repeatable flow, not a one-off script.

Customer zero. Initiate customer zero. An internal DXC department becomes the first real subject. We secure a sponsor and consent, run real interviews, and produce a draft scorecard inside the window.

This is an internal proof, not a public launch. Scale, polish, and the public web flow are deliberately out of scope and come after.

MVP scope

Build the thinnest slice that proves all three outcomes on the MeridianFS fixture and on one internal subject. One interview type, one path through the engine, one scorecard.

In scope

One interview type: AI Readiness, with its six objectives and anchored rubrics hand-authored from Companion 01.

The run-time loop: intake and consent (RUN1), persona (RUN2), planner (RUN3), questioner (RUN4), probe (RUN5), capture (RUN6), with two-pass pacing. Chat first, then ElevenLabs voice on the demo path.

Research, minimal: SEC EDGAR (RES1) and news (RES2) feeding triangulation. Tech-stack (RES3) only if time allows.

Synthesis and scoring (SYN2) scoring directly from interview evidence and research against the anchored rubrics: six-dimension 0-100 scores, reasoning before score, per-dimension confidence. No separate analytical tool. Industry pattern (SYN1) as a placeholder.

Quick wins (SYN3) against a five-pattern subset of Companion 02, enough to prove selection.

Output: the scorecard rendered to PDF (radar, strengths and gaps, representative quote, light value-difficulty 2x2, quick wins, walled recommendation) with the validation checks (OUT2).

A minimal partner review step: approve or adjust before the scorecard is final.

Thin UI: a basic intake form, the chat-and-voice interview interface, a minimal partner review screen, and scorecard delivery by secure link. Internal-tool or low-code where it saves time.

Consent capture for C-1 and C-2 at intake, with legal-reviewed copy.

The MeridianFS fixture seeded and validated end to end.

Out of scope, deferred

The public-facing prospect web flow and 24-hour SLA hardening.

The Interview Designer agent (DES1); the definition is hand-authored.

Competitor (RES4) and regulatory (RES5) research; the full 15-pattern quick-wins library; populated industry pattern content.

Post-delivery agents (routing, benchmark, feedstock) and the benchmark database.

Calibration to a full gold set, multi-stakeholder interviews, and the interactive scorecard.

The thin slice

One respondent answers the six-objective interview in chat or by voice. The engine paces, probes, and captures evidence. Research runs in parallel. The scorer produces six 0-100 scores with reasoning. The scorecard renders. A partner reviews and approves. That single path, working reliably on the fixture and on the customer-zero subject, is the MVP.

Agents in the MVP

Fourteen of the twenty-one agents are in the MVP, enough to run the thin slice end to end. The design-time Designer, the later research agents, and the post-delivery agents are deferred.

| ID | Agent | Role in the MVP |
| --- | --- | --- |
| RUN1 | Intake and Consent | Validate the submission and capture C-1 and C-2 consent. |
| RUN2 | Persona Inference | Infer the respondent persona to adapt the interview. |
| RUN3 | Planner | Select the next objective; run two-pass pacing. |
| RUN4 | Questioner | Generate the next question, in chat or voice. |
| RUN5 | Probe | Decide follow-up versus advance. |
| RUN6 | Capture | Extract evidence signals from each answer. |
| RES1 | Filings and Financials | SEC EDGAR signals for triangulation. |
| RES2 | News and Events | GDELT and news signals. |
| RES3 | Tech-stack Inference | Public stack signals. Conditional, only if time allows. |
| SYN1 | Industry Pattern | Placeholder in the MVP; APR pattern content comes later. |
| SYN2 | Synthesis and Scoring | Six-dimension 0-100 scoring against the rubrics. The core agent. |
| SYN3 | Quick Wins | Select two or three from the five-pattern subset. |
| OUT1 | Output Generation | Render the scorecard and findings appendix. |
| OUT2 | Validation and QA | Run the checks before partner review. |

Deferred from the MVP: DES1 (the definition is hand-authored), RES4 competitor and RES5 regulatory research, and POST1 to POST3 (routing, benchmark, feedstock).

Customer zero

Customer zero is an internal DXC department that agrees to be the first real subject. It proves the process on real people, not just a fixture, and it gives the team a genuine scorecard to learn from. Initiation, not completion, is the three-week target.

Week 1: identify a willing department and secure an executive sponsor; confirm internal consent is simple and fast.

Week 2: scope the subject, tailor any industry framing, and schedule one to three respondents.

Week 3: run the interviews, produce a draft scorecard, and take it through partner review. Capture what the process taught us.

Workstreams and team

Three engineering workstreams plus a thin front-end track run in parallel, with the working group owning content and operations. With three engineers, fold the front-end into the Engine track and use an internal-tool or low-code approach to keep it light; protect the scoring track.

| Workstream | Focus | Who |
| --- | --- | --- |
| A. Engine | Run-time loop RUN1 to RUN6, orchestrator, two-pass pacing, ElevenLabs voice. | Engineer 1 and 2 |
| B. Research and scoring | RES1 filings, RES2 news, SYN2 rubric scoring direct from evidence (no external tool). | Engineer 3 |
| C. Output and review | Scorecard render, OUT2 checks, the partner review step. | Engineer 4 with Robb (design) |
| D. Content and operations | Interview definition authoring, consent copy and Legal, customer-zero setup, demo storyboard. Quick-wins subset and APR-seeded patterns owned by Robb. | Working group (Chris, Shawn); Robb (quick wins) |
| E. Front-end (thin) | Intake form, chat-and-voice interview UI, minimal partner review screen, scorecard delivery link. Internal-tool or low-code for V0. | Engineer 1 (shared with Engine) |

The three-week plan

Week 1: foundations and first walk

Day 1 to 2: confirm the PRD V5 recommended tech stack and NFR targets (see the PRD Technical Requirements section) rather than deciding from scratch; provision the AWS environment; obtain Anthropic and ElevenLabs keys; scaffold the repo and the orchestrator skeleton.

Author the AI Readiness definition: six objectives with anchored rubrics, from Companion 01. Owner: working group.

Stand up the SYN2 scoring scaffold: rubric-based scoring directly from captured evidence and research. No external analytical tool.

Draft the consent copy and send it to DXC Legal. Identify the customer-zero department and approach a sponsor.

Build the five-pattern quick-wins subset (Owner: Robb, APR-seeded) and seed the MeridianFS fixture.

Stand up the intake form and a chat interface shell (internal-tool or low-code).

End of week 1.  The chat loop walks at least one objective end to end on MeridianFS, and the scorer returns a number against a rubric.

Week 2: the vertical slice works

Complete the run-time loop across all six objectives in chat, with two-pass pacing inside the time budget.

SYN2 scores from captured evidence with reasoning before score; RES1 and RES2 feed triangulation; SYN1 runs as a placeholder.

OUT1 renders the scorecard (radar, strengths and gaps, quote, quick wins, walled recommendation); OUT2 runs the checks; the partner review step works.

Integrate ElevenLabs voice on the demo path, with chat as the fallback, including the voice interface (microphone, playback, live transcript) and a minimal partner review screen.

Customer zero: sponsor and consent secured; respondents scheduled; framing tailored.

End of week 2.  End to end on MeridianFS, in chat and voice, to a draft scorecard and partner review. Internally demoable.

Week 3: harden, demo, initiate customer zero

Reliability pass on the demo path; validate the MeridianFS fixture fully and the other two if time allows.

Tune voice turn latency to a natural target; confirm the chat fallback.

Make the partner review usable at 15 to 30 minutes.

Run the customer-zero interviews; produce a real draft scorecard; take it through partner review.

Finalize the demo storyboard and run a dry run; deliver the internal demo to leadership.

End of week 3.  An internal demo proving the technology and the process, and customer zero initiated with interviews run and a draft scorecard in review.

Critical path and dependencies

AWS environment and the Anthropic and ElevenLabs keys, week 1, day 1 to 2. Owner: Chris with Andre.

Tech stack confirmed against the PRD V5 recommended defaults, day 3. Owner: engineering lead.

The authored interview definition, end of week 1. Gates the run-time loop. Owner: working group.

SYN2 scoring scaffold, week 1 to 2. Scores directly against the rubrics from evidence and research; no external analytical dependency.

Consent copy and Legal review, week 1 to 2. Gates any real interview, including customer zero.

Customer-zero sponsor commitment, week 1. Gates the customer-zero interviews in week 3.

Risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Voice latency or integration slips | Build chat first; integrate voice in week 2; keep chat as the demo fallback. |
| Public research is thin for the internal customer-zero subject | Lean on interview evidence for the internal subject; research mainly proves the pipeline, not the internal score. |
| Scores are not yet calibrated | Anchored rubrics and reasoning before score; the partner review gate; accept demo-grade, not calibrated, and start a small gold set. |
| Consent or Legal timing | Draft copy in week 1 and send to Legal at once; customer zero is internal, which simplifies consent. |
| Customer-zero sponsor unavailable | Secure the sponsor in week 1; choose a willing department; scope to one to three respondents. |
| Scope creep | Freeze the MVP scope. Anything off the thin slice goes to the next phase. |

Definition of done

The engine conducts the AI Readiness interview end to end, in chat and voice, on the MeridianFS fixture, inside the time budget.

SYN2 produces six 0-100 scores with reasoning and confidence; OUT1 renders a brand-compliant scorecard; OUT2 passes; a partner reviews and approves.

Customer zero is initiated: a sponsor and consent, interviews run, and a real draft scorecard in partner review.

A repeatable internal demo script exists and has been run for leadership.

What this sets up

Clearing this three-week bar proves the technology and the process and produces the first real result. It feeds the next phase directly: hardening the pipeline, populating the industry patterns and the full quick-wins library, extending the partner review, and moving from customer zero to the first external pilots. It also gives the investor-day story a working system and a real scorecard to show, not a mockup.